## Slide 1
DataHub Modernization
Progress update — from built to running
Phase 2 finished, the parallel stack ran end to end for the first time — and running it caught a cross-tenant data exposure before it reached a customer.
22 commits since the last deck · ~17,500 lines · one linear history on ba/rearch · 17 August 2026

## Slide 2
WHERE THE LAST DECK LEFT OFF
Three domains built. None of them served a request.
What was in place
as of the 12 August deck
▸ Better Auth adopted. ADR-0007; DB-backed sessions, httpOnly cookies.
▸ The core trio. companies · users · folders, each behind an env flag.
▸ 115 api tests, ~91% coverage. integration tests against real Postgres.
▸ main frozen. every change lands on the re-architecture branch.
What that deck said came next
quoted from its closing slide
“Deploy to a real environment and flip the flags … then retire the legacy handlers after a green soak.”
“uploads / requests / messages → reports → quickbooks → extraction.”
Both halves happened. The domains got built — and the attempt to flip a flag found that the cutover mechanism did not work at all.

## Slide 3
THE HEADLINE
Three things, and the third is why the second mattered
01
Phase 2 build complete
▸ uploads · requests · messages plus the first reports slice.
▸ Eight domains + the gateway. same blueprint, same flag pattern.
▸ 115 → 241 api tests. coverage held above 90% on new code.
02
The stack runs end to end
▸ First working cutover. a module answered a real request; legacy kept the rest.
▸ Getting there exposed five defects in the cutover mechanism itself.
▸ One command brings it up. SPA → gateway → legacy → Postgres, seeded.
03
Running it found real bugs
▸ Brokers could read every tenant. would have shipped at the first flip.
▸ Two silent parity defects. a filter ignored; a column name divergence.
▸ None were findable by more unit tests. they needed a running stack.
And a fourth, off to the side: the whole product was mapped for the first time — 93 features, 21 capabilities, one acyclic dependency graph — and it changed the order we should be cutting domains over in.

## Slide 4
PHASE 2 · COMPLETE
Four more domains, ported at parity behind the gateway
uploads
files + documents
▸ Blobs in Postgres bytea behind a StoragePort — S3 swaps in later.
▸ Documents under folders, tenant-guarded via the folder's company.
▸ Append-only document activity.
requests
broker ↔ client work
▸ Priority drives reminder cadence — critical/high 1d, medium 2d, low 7d.
▸ Transactional bulk create.
▸ Approval, narrative upsert, doc links.
messages
in-app comms
▸ Company, 1:1 and group threads.
▸ Member-only posting — or a broker/admin on the group's company.
▸ Unread via a read watermark.
reports
first decomposition slice
▸ Key-report version lifecycle — the backbone entity.
▸ One official version per company, held by a transactional invariant.
▸ The 9,088-line GL engine stays on legacy behind a port that returns 501.
Every domain mounts behind <DOMAIN>_MODULE_ENABLED — off falls through to legacy, so each is reversible in one environment variable. reports is deliberately a slice, not a domain: the safe way to dismantle a 9k-line service is one seam at a time.

## Slide 5
FROM BUILT TO RUNNING
Nine domains built. The flag that turned them on was a no-op.
What the first real attempt found
none of this was visible from the test suite
▸ All 69 module routes were unreachable. Modules sat under /api/*; the SPA calls /auth/login and /companies. Flipping any flag changed nothing.
▸ /api/auth/* is QuickBooks, not our auth. Mounting there also 401'd the OAuth routes and consumed their request bodies.
▸ There was no runnable build. node dist/server.js died resolving TypeScript source — the program had never produced a running artifact.
▸ backend/sql/schema.sql cannot build a database. It indexes a column its own table never declares.
▸ A mistyped flag silently meant “off.” Clean boot, no cutover, no signal.
What shipped, and what it proved
the first working cutover in the program
▸ Per-route middleware instead of router-level, so unflipped paths fall through clean.
▸ Modules re-mounted on the real legacy contract; the SPA now talks to the gateway.
▸ A deployable artifact. Dockerfiles, compose stack, strict env validation.
▸ Two standing guards. One derives the legacy and module route surfaces from source and fails the build on a mismatch; the other pins fall-through.
▸ Verified under compose. /auth/login answered by the TypeScript module while /api/auth/status still proxied to legacy — then flag off, back to legacy.

## Slide 6
HOW WE WILL KNOW IT IS SAFE
The evidence machinery, built once and reused
The parity harness
same gateway, flag off then on
▸ Replays one request against both engines, isolating exactly what a cutover changes, then normalises and diffs.
▸ Noise control is the whole game. A harness that reports differing ids gets ignored — which is worse than not having one.
▸ Two were built independently; the weaker one was deleted. Two harnesses for one job is worse than either. 73 tests.
What authorises a flip
and what does not
▸ The request set is derived from source, never hand-listed — adding a route widens what parity must prove, and a stale derivation fails the build.
▸ Two refusals before any request: not a production host, and the staging marker must be present. Exit 3 means “declined”, not “disagreed”.
▸ Coverage prints with every verdict. Today the declared suite compares 22 of 68 endpoints — so no run can read as “parity proven.”
One-command demo stack
the whole path a user takes
▸ SPA → gateway → legacy → Postgres, seeded, in one script.
▸ Verifies ten behaviours on boot, including tenant scoping and QuickBooks fall-through.
▸ Three personas, three companies — one owned by nobody, so cross-tenant denial is demonstrated, not assumed.
A clean run is evidence for a flag flip, not proof of parity — and it now says how much it actually looked at. The flip criteria separate what authorises a reversible flip from what authorises deleting a handler, which is not reversible.

## Slide 7
WHAT RUNNING IT CAUGHT
Defects that no amount of unit testing would have found
SECURITY · found by the demo stack's own boot check
Every broker could read every tenant's company
The shared access guard short-circuited role === "broker" to true; legacy grants blanket access to admins only. All seven domains route their tenant check through that guard, so the first flip would have handed every broker read access to every other tenant — on a platform whose tenants are competing sellers in the same process. Listing endpoints were scoped correctly, which is why it only surfaced on a direct fetch by id.
Two in the product
wrong answer, clean response
▸ An archived-view filter was ignored. The SPA sends includeArchived; the modules read include_archived. The query parsed cleanly and returned the unfiltered list.
▸ A document-activity column divergence. The module writes action/actor_id/at; legacy reads activity_type/user_id/created_at.
Two in the checking itself
the apparatus got audited too
▸ A scenario asked for a path neither engine serves. Both 404'd, so it reported a match — while its whole purpose was to observe an expected difference.
▸ “PARITY CLEAN” printed either way. 22-of-68 endpoints and 68-of-68 read identically until coverage was measured.
And one we can now prove
rather than assert
▸ Production's schema is not recoverable from this repository. One table is created twice with conflicting definitions, both guarded by IF NOT EXISTS — which one production has depends on the order two migrations ran in.
▸ That is the argument for reconciling from a snapshot, now demonstrated.

## Slide 8
BUILT NEW · SE-0004
The activity log — the one capability whose value expires
Why now, and why greenfield
activity not recorded when it happened is gone
▸ Buyer-engagement analytics is built entirely from history. Retrofitting yields a log with no past.
▸ It has no legacy equivalent. Nothing to cut over, no parity to prove, no handler to delete — so it does not compete with the cutover work.
▸ Capture is two-tier. A request envelope written at the gateway for every request, legacy-proxied included, plus typed events from migrated modules, joined by correlation id. Neither tier alone is sufficient.
How it is made trustworthy
and where the honesty limits are written down
▸ Immutability enforced twice. No update or delete method exists, and the app's database role lacks both grants — tested by asserting the refusal.
▸ Failure is visible, not silent. On overflow the writer records a gap marker — interval, count, reason — rather than dropping records.
▸ 95.9% coverage; emission tested against the real routers, which caught an ordering bug that would have logged document opens that were actually denied.
▸ The read surface is deferred on purpose. Search and export can be built over history; history cannot be built later.

## Slide 9
THE PRODUCT SURFACE, MAPPED
93 features, 21 capabilities, one dependency graph
What the map says
the first document describing the whole product
▸ Every feature placed in one capability, written as behaviour that can fail rather than intent.
▸ 49 dependency edges, acyclic, computed into eight layers — so build order is derived, not argued.
▸ Four capabilities gate the rest. Two of them were not scheduled at all.
▸ Roughly 80% of the intended product does not exist yet. That is a number the business has not previously had to look at.
▸ Fifteen feature IDs are referenced but missing. Nine look clerical; six describe capabilities nobody has written down.
Why that is good news for the rewrite
the two programs do not compete this phase
▸ Six of the eight foundation capabilities are domains we have already built and never turned on. The work there is cutover, not build.
▸ So Phase C buys migration progress and product foundation with the same money — provided we flip domains in the graph's order rather than the legacy code's shape.
▸ Two amendments to the old order: the activity log moves first, and the QuickBooks data-retrieve wizard moves up from second-to-last, because it is the write path feeding 39 features.
▸ That wizard is now specced to implementation fidelity — 14 requirements, 40 scenarios — as the worked example of the depth each feature gets when scheduled.

## Slide 10
BY THE NUMBERS
Since the last deck, five days ago
9
domains built
seven domains, the reports slice, and the gateway
241
api tests green
up from 115; plus 40 db and 73 in the harness
22 / 68
endpoints under parity
every domain partial: folders 3/13, uploads 2/9
3
product defects caught early
one a cross-tenant exposure; two more found in the harness itself
0
domains in production
the number this phase exists to change
The last column is the honest one. Every other number describes work that is finished, tested and reversible — and until a domain serves real traffic and its legacy handler is deleted, the parallel rewrite is pure cost: two implementations to maintain, one of them unused. That is the program's standing risk #1, and Phase C's only real objective.
One local datapoint on what flipping buys, with its caveat: in the demo stack a client login takes ~0.7s through the modules against ~49s through legacy, because legacy reaches for Supabase on every read. No Supabase credentials are configured there, so treat it as a shape, not a benchmark.

## Slide 11
WHERE WE GO NEXT
Phase C — turn it on, then delete what it replaced
The sequence
only two hard ordering constraints
▸ C1 · Staging from a production snapshot. Reconcile the drift, record a baseline, verify session-secret parity before anything flips.
▸ C2 · Flip auth, then delete its legacy handlers. Widen the parity suite past today's 22 of 68 endpoints, canary, soak, and a rollback exercised deliberately rather than assumed.
▸ C3 · The foundation domains, in graph order. companies → users → folders (this is access control), then uploads, then the reports slice.
▸ C4 · Activity capture, starting now. It depends on nothing and its value expires fastest.
What we need from outside engineering
decisions, not capacity
▸ The financial-data table structure. Highest-leverage item on the list: it gates 39 features, and flipping reports before it is settled means paying the cutover cost twice.
▸ The rule for customer data in staging. The snapshot carries real financials and PII, and staging sends real email. Anonymise, or treat staging as production for access. This is a decision, not a task.
▸ Two product boundary calls on notifications, document versioning, and the deal-structure engine that six features reference and no row defines.
▸ No durations in this plan. There is no velocity data for this team yet; estimates belong to the people doing the work, attached to these exit criteria.

## Slide 12
The stack runs, and running it made us safer.
Next: one domain serving production traffic, with its legacy handler deleted. Nothing else in Phase C counts until that happens.
Details: docs/REARCH_LOG.md §§14–21 · docs/PHASE_C_PLAN.md · docs/CUTOVER_FLIP_CRITERIA.md · openspec/changes/centuriuum-product-surface